## Sheet1
Table 1. Checklist for Managing Archaeological Collections. | Done? | Stakeholders Involved
STAGE 1: PROJECT SCOPE AND PROGRAMMING/PLAN/ BUDGET/AGREEMENTS/FUNDING:
Have a strong understanding of relevant federal/state/local laws that govern ownership and long-term care of resulting collections. |  | 1, 2, 3, 6, 7
Identified the repository where the collection will be housed, and communicated with repository personnel. |  | 1, 2, 3, 6, 7
Programmed the associated costs for collections into the project budget, including curation fees and conservation costs. |  | 3, 6
Considered the appropriate type of contract to award, which recognizes a collection will be created (e.g., fixed price, cost-reimbursable, time and materials with 'not to exceed' or 'cost plus' options). |  | 3, 6
Developed a scope of work that includes tasks related to recovered artifacts and associated records as specified in the Request for Proposal. |  | 1, 2
Have a collections strategy that considers culling and sampling, in-field analysis, and/or object reburial, as applicable. |  | 1, 2
Have a curation budget, including line items for supplies, repository fees (objects and records), conservation, and other related costs. *Make sure to include a contingency provision if significantly more artifacts are recovered than outlined in the collection strategy.* |  | 1, 2
Obtained all permits necessary to begin an archaeological project. |  | 1, 2
Clarified collection ownership and responsibilities of all stakeholders. If you are working on private land, have you obtained a Deed of Gift? |  | 1, 2
Secured a curation agreement that clearly states the obligations of all parties, and obtained the repository's acceptance standards. |  | 1, 2, 3, 6, 7
Identified/Secured/Provided funding for analysis, report writing, curation supplies, repository fees, and long-term curation (including future enhancements). |  | 1, 2, 3, 6, 9
STAGE 2: FIELDWORK:
Carried out your collecting strategy and considered it to account for significantly more recovered artifacts. |  | 1, 2
Developed protocol for tracking artifacts from the field to the lab.
STAGE 3: PROCESSING/ANALYSIS/REPORTING:
Conducted thorough analysis and prepared a report. |  | 1, 2
Identified in the report and SHPO site files where collections are curated and what objects were sampled/culled/removed for destructive analysis. |  | 1, 2, 3
Taken steps to make the report, or parts thereof, accessible to interested parties. |  | ALL
STAGE 4: CURATION PREPARATION:
Analyzed, cataloged, packed, labeled, and prepared collections according to repository standards. |  | 1, 2
Prepared digital associated records with required metadata for upload onto server space, and labeled all digital photos and files. |  | 1, 2
Identified objects in need of conservation and followed through on a plan for treatment. |  | 1, 2
Delivered the collection to the designated repository. |  | 1, 2, 3, 5, 6
STAGE 5: REPOSITORY ACCEPTANCE:
Agreed to accept a collection for curation, ensuring that it will be accessioned, cataloged, properly stored, and accessible for future use. |  | 7
Invoiced for the curation fees, as applicable.
Ensured that the accessioning and cataloging information is accurate and complete, including the owning party who is accountable for the collection.
Obtained a repository agreement for long-term care of collections. |  | 3, 7
STAGE 6: ACCESS/USE:
Taken steps to ensure the collection will remain accessible for future use, including providing information on the internet about where it is curated. |  | ALL
STAGE 7: MAINTENANCE:
Made arrangements for and carried out regularly scheduled inventories and inspections and a plan for long-term curation and conservation treatments. |  | 3, 7
Migrated digital data to updated formats. |  | 1, 2, 3, 7
STAGE 8: ENHANCEMENTS:
Evaluated collections to determine if they need enhancements such as rehousing, conservation, or digitization. |  | 1, 2, 3, 7
STAGE 9: DEACCESSIONING:
Identified collections or portions of collections that are candidates for deaccessioning. |  | 1, 3, 4, 7
Followed through on protocols required in appropriate laws and regulations. |  | 1, 3, 4, 7
Key: Major Stakeholders (corresponding numbers are listed in the far right hand column).
1. Academic and CRM archaeologists 2. Students 3. Federal/Tribal/State/Local government agencies 4. Tribes and descendant communities 5. Private landowners
6. Developers 7. Repository personnel 8. Professional organizations 9. Granting institutions 10. The media 11. The general public